## Backlog
Product Backlog — feature cards
Falcon Eye · عين الصقر — Product Management · v0.2 · 5 Oct 2026
ID | Epic | Feature | Problem | User | User story | Expected value | Pillar | Priority | MVP scope | Acceptance criteria | Dependencies | Design status | Dev status | Testing status | Product status | Owner | Release
F-01 | E1 Capture | Rolling 30s buffer per camera | Nothing can be replayed unless the last moments are always held. | System | As a player, I want the last 30 seconds to always be available, so that any moment can be saved after it happens. | Core value — without it there is no product. | See | P0 Critical | Must | Both cameras buffered continuously for 4h with no gaps; no re-encode (stream copy); CPU < 70% on the chosen edge box. | F-03 edge box decision; RTSP from DS-2CD cameras | N/A | In progress | Not started | Development | Tech | Prototype
F-02 | E1 Capture | Cut & save clip on trigger | A press must turn into a playable file fast enough to feel instant. | Player | As a player, I want my clip ready within seconds of pressing, so that I can watch it before the next attack. | Defines the 'instant' promise. | See | P0 Critical | Must | p95 press→clip ready ≤ 10s over 200 test presses; clip covers both angles; MP4 plays on iOS Safari + Android Chrome. | F-01, F-05 | N/A | In progress | Not started | Development | Tech | Prototype
F-03 | E1 Capture | Production edge box decision | Files name 3 different computers; Pi Zero 2 W (512MB, no Ethernet) likely too weak for 2× 4K streams. | Ops | As ops, I want one tested edge box spec, so that every install is the same and reliable. | Removes the biggest reliability risk before the pilot. | See | P0 Critical | Must | Bench test Pi Zero 2 W vs Pi 5 vs N100 on sub-stream + main-stream; pick one; document spec + cost. | Hardware on hand (Pi arriving) | N/A | Not started | Not started | Ready for Development | Tech | Prototype
F-04 | E1 Capture | Offline-first local operation | Venue internet drops; replay must not depend on it. | Player | As a player, I want replay to work even if the internet is down, so that the moment isn't lost. | Reliability promise made on the website FAQ. | See | P0 Critical | Must | With WAN unplugged: presses still save clips locally; on reconnect, clips upload and links go live within 2 min. | F-01, F-02, F-08 | N/A | Not started | Not started | Ready for Development | Tech | MVP
F-05 | E2 Trigger | Physical button per goal | Players won't open an app mid-game; a physical button is the whole UX. | Player | As a player, I want one big button by the goal, so that saving a moment takes one second. | Zero-friction trigger = engagement. | Act | P0 Critical | Must | IP65+ metal button on side fence ~2m from goal; wired via GPIO/USB board (not pynput); 2s debounce; each button maps to pitch + goal. | F-03 | Not started | In progress | Not started | Development | Tech | Prototype
F-06 | E2 Trigger | Press feedback (light / sound) | Without feedback players don't know if the press worked and press again. | Player | As a player, I want a light or beep when I press, so that I know it saved. | Trust in the button; fewer double clips. | Understand | P1 High | Should | LED blinks within 300ms of press; distinct pattern if save failed. | F-05 | Not started | Not started | Not started | Idea | Tech | MVP
F-07 | E3 Clip delivery | QR pitch page | The button has no phone attached — the clip must reach the right players. | Player | As a player, I want to scan the sign at my pitch and see tonight's clips, so that I can find mine without an account. | Solves delivery without app or sign-up. | See | P0 Critical | Must | Fixed QR sign per pitch opens a page listing clips from the current booking window (newest first); loads < 2s on 4G. | F-08, F-15 | Not started | Not started | Not started | Ready for Design | Design | MVP
F-08 | E3 Clip delivery | Clip page + share link | The clip is the product the player sees and spreads. | Player | As a player, I want to watch, save and send my clip, so that the squad sees it on WhatsApp. | Activation + viral loop (each share is an ad). | Act | P0 Critical | Must | Play, download MP4, native share sheet; link preview shows thumbnail + venue name; works with no login. | F-02, KSA cloud hosting | In progress | In progress | Not started | Design | Design | MVP
F-09 | E3 Clip delivery | Angle A/B switch | One angle often hides the ball. | Player | As a player, I want to switch cameras, so that I can see the clearest view. | Better clip quality; settles disputes. | Understand | P1 High | Should | Toggle between Camera A/B on the same timeline in < 1s. | F-02 | Done | Not started | Not started | Ready for Development | Tech | MVP
F-10 | E3 Clip delivery | Slow-mo & frame step | Disputes (in/out, foul) need detail. | Player | As a player, I want slow motion, so that we can settle whether it went in. | The 'VAR' moment. | Understand | P1 High | Should | 0.25×/0.5× playback and ±1 frame step on mobile. | F-08 | Done | Not started | Not started | Ready for Development | Tech | MVP
F-11 | E3 Clip delivery | Venue watermark on clips | Venue gets no brand value when clips are shared. | Buyer | As a venue owner, I want my logo on every clip, so that each share advertises my pitch. | Direct buyer value — free marketing. | Act | P1 High | Should | Venue logo + 'Falcon Eye' mark burned or overlaid on downloads; toggle per venue. | F-02 | Not started | Not started | Not started | Idea | Design | Pilot
F-12 | E3 Clip delivery | One-tap clip rating | We need player satisfaction data without surveys. | Player | As a player, I want to rate the clip in one tap, so that the venue knows we like it. | Pilot KPI (CSAT) source. | Understand | P1 High | Should | 👍/👎 or 1–5 under the clip; stored anonymously; 1 rating per device per clip. | F-08 | Not started | Not started | Not started | Idea | Product | Pilot
F-13 | E4 Venue console | Device status (cameras & buttons) | Venue staff can't tell if the system is working until a player complains. | Admin | As a venue supervisor, I want to see that cameras and buttons are online, so that I fix issues before kickoff. | Reliability + fewer support calls. | See | P1 High | Should | Green/red per device updated every 30s; last-seen time; works on phone. | F-16 | Done | Not started | Not started | Design | Tech | MVP
F-14 | E4 Venue console | Nightly stats (clips per pitch / hour) | Venue can't see the value they're paying for. | Buyer | As a venue owner, I want to see clips, opens and shares per pitch, so that I know players use it. | Proves ROI → renewal. | Understand | P1 High | Should | Daily/weekly counts: presses, clips opened, shares, by pitch & hour. | F-17 | Done | Not started | Not started | Design | Product | Pilot
F-15 | E4 Venue console | Pitch & booking window setup | Clips must be grouped by booking so groups only see their own session. | Admin | As a venue supervisor, I want to set pitch names and session times, so that each group sees its own clips. | Privacy + correct delivery. | Act | P0 Critical | Must | Pitch names editable; default hourly windows; clips older than the current window hidden from the QR page. | F-07 | Not started | Not started | Not started | Discovery | Product | MVP
F-16 | E5 Ops & reliability | Heartbeat monitoring + alerts | We must know a pitch is down before the venue does. | Ops | As Falcon Eye ops, I want an alert when a camera, button or edge box goes offline, so that we fix it fast. | Uptime guardrail. | Act | P0 Critical | Must | Heartbeat every 60s; alert to ops (WhatsApp/Telegram) within 5 min of outage during opening hours. | F-03 | N/A | Not started | Not started | Ready for Development | Tech | MVP
F-17 | E5 Ops & reliability | Event logging & analytics | Pilot KPIs need data: presses, ready time, opens, shares. | Product | As product, I want every press/open/share logged, so that we can measure the pilot. | Without it the pilot can't be judged. | Understand | P0 Critical | Must | Events: press, clip_ready (with latency), page_view, clip_play, download, share, rating — with pitch + time. | F-02, F-08 | N/A | Not started | Not started | Ready for Development | Tech | MVP
F-18 | E5 Ops & reliability | Install kit & install checklist | Install is part of the product; a bad install = a bad product. | Ops | As an installer, I want a step-by-step checklist, so that every pitch is installed the same way in one visit. | Repeatable installs → scale. | Act | P0 Critical | Must | Checklist covers mount height/angle, cabling, power, network, button placement, test 10 presses; install time recorded. | F-03, F-05 | Not started | N/A | Not started | Ready for Product | Ops | Pilot
F-19 | E6 Trust & privacy | Auto-delete after 24h | Storing player video longer than needed creates PDPL and trust risk. | Player | As a player, I want clips to disappear after a day unless saved, so that I'm not filmed forever. | Trust + compliance + low storage cost. | Act | P0 Critical | Must | Clips and thumbnails deleted from edge + cloud 24h after creation (configurable later); deletion logged. | F-08 | N/A | Not started | Not started | Ready for Development | Tech | MVP
F-20 | E6 Trust & privacy | Filming notice signage + privacy page | Players must know they're on camera and what is kept. | Player | As a player, I want a clear notice at the pitch, so that I know what's recorded and for how long. | PDPL transparency; prevents complaints. | Understand | P0 Critical | Must | AR/EN sign at pitch entrance + QR to privacy page (what, why, 24h, who to contact). Legal review before pilot. | Legal input | Not started | N/A | Not started | Ready for Design | Design | Pilot
F-21 | E6 Trust & privacy | Venue posting with consent | Website promises venues can post clips with players' consent — no flow exists. | Buyer | As a venue owner, I want to post the best clips with permission, so that I get content without complaints. | Marketing value with compliance. | Act | P2 Medium | Later | Player can mark a clip 'OK to share' on clip page; venue sees only consented clips in a 'Content' tab. | F-08, F-14 | Not started | Not started | Not started | Idea | Product | V1
F-22 | E7 Commercial & pilot | Auto pilot report | The pilot ends with a decision; the venue needs evidence on one page. | Buyer | As a venue owner, I want a report after the pilot, so that I can decide to buy. | Converts pilots to paid. | Understand | P1 High | Should | One-page PDF/HTML: presses, % bookings with a press, opens, shares, uptime, top moments, before/with comparison. | F-17 | Not started | Not started | Not started | Idea | Product | Pilot
F-23 | E7 Commercial & pilot | Pricing & packages | Deck says 30 SAR per booking; site says priced per pitch. One model is needed before selling. | Buyer | As a venue owner, I want a simple price, so that I can compare it to what it brings. | Unblocks sales. | Act | P0 Critical | Must | Two packages tested in ≥ 8 venue interviews; one chosen and written in a price sheet; deck + site aligned. | Discovery interviews | N/A | N/A | N/A | Discovery | Founder | Pilot
F-24 | E8 Intelligence | Player accounts / My clips | Returning players may want a history of their clips. | Player | As a regular, I want all my clips in one place, so that I can find old goals. | Retention — only if pilot shows repeat use. | See | P2 Medium | Later | Phone-number login (OTP); clips saved to account bypass 24h delete. | F-19 policy update | Done | Not started | Not started | Idea | Product | V1
F-25 | E8 Intelligence | Booking-app integration | Sending clips by WhatsApp to the booker needs booking data. | Player | As the booker, I want the session's clips sent to me automatically, so that I don't need to scan. | Removes QR step; deeper venue lock-in. | Act | P3 Later | Later | Pull booker phone + slot from the venue's booking system; send WhatsApp with session link after the game. | Venue booking system API | Not started | Not started | Not started | Idea | Tech | V1
F-26 | E8 Intelligence | Auto highlight reel per session | Groups want a short reel of the night, not single clips. | Player | As a group, I want a 60s reel of our night, so that we post one video. | Shareable content; possible premium. | Act | P3 Later | Later | Reel stitched from session clips with venue branding, ready 10 min after session end. | F-02, F-15 | Not started | Not started | Not started | Idea | Tech | V1
F-27 | E8 Intelligence | AI ball tracking / follow-cam | Wide shots make the ball small; AI detection is at 72% in tests. | Player | As a player, I want the clip to follow the ball, so that it looks like TV. | Quality upgrade; not needed for replay. | Understand | P3 Later | Later | Detection ≥ 90% from a high central mount before any build; runs on Jetson add-on. | High-mount recording; Jetson | N/A | In progress | Not started | Discovery | Tech | Scale
F-28 | E8 Intelligence | Auto goal detection (no button) | Players forget to press. | Player | As a player, I want goals saved automatically, so that nothing is missed. | Removes trigger dependency — research only. | See | P3 Later | Later | Research spike only after F-27 proves detection. | F-27 | N/A | Not started | Not started | Idea | Tech | Scale
F-29 | Out of scope | Full-match recording / live streaming | Different product (Veo-style), big storage + privacy cost. | Player | — | Not our core job. | See | P3 Later | Out of Scope | — | — | N/A | N/A | N/A | Idea | Product | Scale
F-30 | Out of scope | Referee/officiating VAR decisions | Formal decisions need rules, operators and liability. | Admin | — | Not our core job. | Understand | P3 Later | Out of Scope | — | — | N/A | N/A | N/A | Idea | Product | Scale
F-31 | Out of scope | Security / surveillance use | Brand and trust risk; product is about football moments. | Buyer | — | Conflicts with positioning and privacy promise. | See | P3 Later | Out of Scope | — | — | N/A | N/A | N/A | Idea | Product | Scale
F-32 | Out of scope | Own booking system | Venues already use booking apps; competing with them distracts. | Buyer | — | Integrate, don't replace. | Act | P3 Later | Out of Scope | — | — | N/A | N/A | N/A | Idea | Product | Scale

## Decision Log
Decision Log
Falcon Eye · عين الصقر — Product Management · v0.2 · 5 Oct 2026
# | Decision | Reason | Date | Impact | Status | Source / owner
1 | Product name: Falcon Eye / عين الصقر (formerly 1/2 Lens VAR) | Distinct, ownable, works in AR + EN | Oct 2026 | Brand | Confirmed | Founder
2 | Tagline: SEE FURTHER / تشوف أبعد | From approved brand board; Saudi dialect | Oct 2026 | Brand | Confirmed | Founder
3 | Bilingual pitch deck (AR + EN in one file) | Arabic and English audiences | Oct 2026 | Commercial | Confirmed | Founder
4 | Discovery before full build | Avoid building features before need is proven | Oct 2026 | Product | Confirmed | Product plan v0.1
5 | Pilot-led go-to-market | Prove value before scaling | Oct 2026 | Product / Sales | Confirmed | Product plan v0.1
6 | Instant replay ships without AI; AI follow-cam is phase 2 | Replay needs no AI; detection only 72% at best angle | Aug 2026 | Product / Tech | Confirmed | Final review deck
7 | Two IP cameras (DS-2CD, RTSP) per pitch, opposite corners | Analog DS-2CE gives no RTSP; two angles cover the ball | Aug 2026 | Tech | Confirmed | Final review deck
8 | Clips stored in a Saudi region; auto-delete after 24h | PDPL + trust + cost | Aug 2026 | Legal / Tech | Confirmed | Final review deck
9 | Venue pays; players free; no app, no sign-up | Players won't pay or install; venue gets differentiation | Oct 2026 | Commercial | Hypothesis — validate in discovery | Deck + website
10 | Clip length = last 30 seconds | Covers a full attack; short to share | Aug 2026 | Product | Hypothesis — validate in pilot (20/30/45s) | Final review deck
11 | Replace Pi Zero 2 W as production edge box (Pi 5 or N100) | 512MB RAM, no Ethernet, 2.4GHz only — too weak for 2× 4K | Oct 2026 | Tech | Proposed — after bench test | Project review (00 Docs)
12 | Button read via GPIO / evdev, not pynput keyboard emulation | pynput needs a desktop session and catches any Enter key | Oct 2026 | Tech | Proposed | Project review (00 Docs)
13 | Clip delivery via fixed QR 'pitch page' per pitch | Button has no phone; QR needs no app or account | Oct 2026 | Product / UX | Proposed — test in prototype | Product plan v0.2
14 | North Star = replays watched per week | Captures press + reliability + delivery in one number | Oct 2026 | Product | Proposed | Product plan v0.2
15 | One pricing model across deck and website | Deck says 30 SAR/booking, site says per pitch | Oct 2026 | Commercial | Open — decide after interviews | Product plan v0.2
16 | Correct deck claim 'almost no competitors in KSA' | ReplayVar (Dammam) already sells button replay for football in KSA | Oct 2026 | Commercial / Brand | Proposed | Market research Oct 2026
17 | Position as 'free for players, no app, just a link' vs ReplayVar's paid player app | Clear wedge against the local rival | Oct 2026 | Marketing | Hypothesis — validate with players | Market research Oct 2026
18 | No face recognition / biometric features at launch | Biometrics = sensitive data under PDPL | Oct 2026 | Legal / Product | Proposed | Market research Oct 2026

## Assumptions
Riskiest assumptions & tests
Falcon Eye · عين الصقر — Product Management · v0.2 · 5 Oct 2026
# | Assumption (we believe…) | Type | Risk if wrong | Evidence today | Test | Success signal | Due | Result
A1 | Players will press the button during a game | Behaviour | High | Padel replay usage (to verify for KSA) | Pilot night at 1 venue; count presses per booking | ≥ 60% of bookings have ≥ 1 press | Pilot week 1
A2 | A clip reaches a phone in ≤ 10s reliably | Technical | High | Prototype works on cloud VM; edge box untested | Bench test 200 presses on chosen edge box | p95 ≤ 10s, failures ≤ 2% | Prototype
A3 | Players find their clip via the QR pitch page | UX | High | None | Hallway test with 5 player groups + pilot night | ≥ 80% of clips opened at least once | Prototype
A4 | Venue owners see enough value to pay monthly | Commercial | High | None documented | 8–10 owner interviews with 2 price options; ask for LOI | ≥ 3 pilot yeses, ≥ 1 LOI at tested price | Discovery
A5 | Replay increases bookings or repeat bookings | Outcome | Medium | Assumed in deck | Pilot: replay pitch vs control pitch, 4 weeks | Measurable uplift vs control (direction + size) | Pilot end
A6 | Players accept being filmed (with notice + 24h delete) | Trust / legal | Medium | None | Signage + privacy page; log complaints | 0 unresolved complaints; legal sign-off | Pilot
A7 | One install takes ≤ 1 day with venue power at floodlight poles | Operations | Medium | Install notes in deck | Time the first 2 installs | ≤ 8h per pitch, no return visit | Pilot
A8 | Hardware cost stays ≤ ~4,400 SAR per pitch | Cost | Medium | BOM range 3,790–6,540 | Price the pilot kit from real invoices | Actual ≤ planned | MVP
A10 | Replay cameras are not covered by the 2022 security-camera law (publishing restrictions) | Legal | High | None — law restricts sharing CCTV footage | Saudi legal opinion before pilot | Written opinion: OK with signage + consent | Discovery
A11 | We can win venues against ReplayVar | Competition | High | ReplayVar exists in KSA; no public clients/prices | Mystery-shop ReplayVar; ask venues if pitched | Clear reason to pick us in ≥ 5 interviews | Discovery
A9 | Venues want the clips as social content | Marketing value | Medium | Website claim | Ask in interviews; track posts during pilot | ≥ 3 posts / week by pilot venue | Pilot

## Pilot KPIs
Pilot KPIs — Before vs With Falcon Eye
Falcon Eye · عين الصقر — Product Management · v0.2 · 5 Oct 2026
KPI | Level | Before Falcon Eye (baseline) | With Falcon Eye | How measured | Target (hypothesis) | Result
Replays watched / week (North Star) | Outcome | 0 |  | clip_play events | Grows week over week
% bookings with ≥ 1 press | Engagement | — |  | press events ÷ venue bookings | ≥ 60%
Clip open rate | Activation | — |  | clips with ≥ 1 play ÷ clips | ≥ 80%
Share rate | Engagement | — |  | share/download ÷ opened clips | ≥ 30%
Press → clip ready (p95) | Guardrail | — |  | clip_ready latency | ≤ 10s
Uptime in opening hours | Guardrail | — |  | heartbeats | ≥ 98%
Failed presses | Guardrail | — |  | press without clip_ready | ≤ 2%
Bookings / week on pilot pitch | Outcome | From venue records (4 weeks before) |  | venue booking records vs control pitch | Uplift vs control
Repeat groups | Retention | From venue records |  | same booker within 14 days | Uplift vs control
Venue social posts using clips | Outcome | Count 4 weeks before |  | venue accounts | ≥ 3 / week
Player satisfaction | Outcome | — |  | one-tap rating on clip page | ≥ 4.3 / 5
Support incidents | Guardrail | — |  | ops log | ≤ 1 / week after week 1
Pilot → paid conversion | Retention | — |  | signed agreement | Venue signs at tested price

## Requests
Request intake (governance) — every new idea starts here
Falcon Eye · عين الصقر — Product Management · v0.2 · 5 Oct 2026
Date | Requested by | Request | What problem does it solve? | For which user? | How important? (P0–P3) | Evidence | Fits current roadmap? | What will we delay? | Decision | Notes
2026-10-05 | Website copy | WhatsApp alerts to venue when a device drops | Venue learns about outages late | Admin | P1 High | Promised on website | Yes — MVP (as ops alert first) | Nothing — ops alert already P0 | Build | Ship to ops first (F-16), venue alert in Pilot
2026-10-05 | Mobile app prototype | Player 'My clips' with history | Find old clips | Player | P2 Medium | None yet | No — needs accounts | Pilot instrumentation | Later | Revisit if pilot shows repeat players

## Lists
Status | Priority | Scope | Step | Pillar | Release | Owner | Decision
Idea | P0 Critical | Must | Not started | See | Prototype | Product | Build
Discovery | P1 High | Should | In progress | Understand | MVP | Tech | Test
Ready for Product | P2 Medium | Later | Done | Act | Pilot | Design | Later
Ready for Design | P3 Later | Out of Scope | N/A |  | V1 | Ops | Reject
Design |  |  |  |  | Scale | Sales/Marketing | Pending
Ready for Development | [5 empty] | Founder
Development
QA
Ready for Release
Released
Measured